## Sheet1
General Schedule
Row | David | Tommy | Khide | William | Sagar | Everyone.
Title | Project Management, QA testing, Game Developer 2 Game Design. Web Dev, backend. | Web Development, QA testing Game Developer 3 | Game Development, Game Design | Graphic art, Story design, | Media, QA tester Advertisement, Presentation, Artist 2
Week 1 - 1 |  |  | Choose Game Engine.
Week 1 - 2 | Scheduling, Tower Design Powerpoint preparation Learn the basic of the game Engine. | HTML page. Study basic features of the game engine. Review Javascript from COMP1527 | Brief tutorial to everyone on the engine itself. Basic UI system and food. | Design the protagonist, Design the logo, Design the game title, | Power Point preparation, 30 sec video (Both Friday) | (WeekEnd job) Learn the basics of the game engine that Khide chose.
Week 2 - 1 | Host the webpage and find the right link for the page. Implement MySQL and some hosting features mentioned in the lecture. Add money feature in the game. | Write the contents on the page. Make Login page, | Finish game prototype, UI design, Game lobby screen, Change UI sccording to the size of the visual that William created. | Design the tower visuals, design background of the game Finish PNG image of the game background, Finish png image of at least half of the towers. | Assist the art part (with William) | Read the code of the actual game and keep up with what's going on.
Week 2 - 2 | Game development | Fill the detailed contents on the page. Finish the page. Game development | Districute workload to the new devleopers. | Finish visuals for all the towers. Design animations, of towers composting food. | Assist the art expert
Week 3 - 1 | Finish first version | Finish first version, QA test the game. | Finish the first version | Final touch on the art. | QA test on the first version | First Version released
Week 3 - 2 |  |  | Take feedback from QA testers and fix.
Week 4 - 1
Week 4 - 2
Week 5 - 1
Week 5 - 2
This schedule can be changed any time according to the actual workload done. Claim for overly imposed workload can be written on slack and schedule can change. QA log link: https://docs.google.com/document/d/1xh_44jDLhRtUZO6BpEWbmFri1WRelBw3NhSJnzZkNZA/edit?usp=sharing